## Sheet1
Task | Start | End | Duration
Project Plan, Initial repository setup (Library/CMake support) | 2021-11-01 | 2021-11-05 | 4
Abstract & Derived Class Implementations | 2021-11-05 | 2021-11-12 | 7
Map, Tower and Enemy class implementations | 2021-11-05 | 2021-11-19 | 14
Map, Tower and Enemy class tests and debugging | 2021-11-15 | 2021-11-26 | 11
Level Editor and Game loop functions | 2021-11-19 | 2021-12-03 | 14
Unit Tests, Debugging | 2021-12-03 | 2021-12-10 | 7
Debugging and Finalize Submissions | 2021-12-10 | 2021-12-12 | 2
Task |  | Duration
Project Plan, Initial repository setup (Library/CMake support) | 0 | 4
Abstract & Derived Class Implementations | 4 | 7
Map, Tower and Enemy class implementations | 4 | 14
Map, Tower and Enemy class tests and debugging | 14 | 11
Level Editor and Game loop functions | 18 | 14
Unit Tests, Debugging | 32 | 7
Debugging and Finalize Submissions | 39 | 2
Start Day